## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 0 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Starting Date: | 2015-10-10 | Deadline: | 2015-12-15
Todays Date: | 2015-12-10 22:41
Days left: | 4.0552
Days used: | 61.9448 | time axis 2015-10-10 to 2015-12-18
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2015-10-10: DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101
Research, Building Concept Idea | 1 | 11 | 1 | 11 | 100%
Server Initialization | 12 | 7 | 12 | 7 | 100%
Domain Name Registration | 12 | 7 | 12 | 7 | 100%
Sketch Designs (UI,Logo,Thinking :) ,etc.) | 19 | 7 | 19 | 7 | 100%
Basic Setup (folders,sftp setup,etc.) | 20 | 13 | 20 | 13 | 100%
Database Setup | 33 | 7 | 33 | 7 | 100%
API Version 1 Development | 40 | 30 | 40 | 30 | 85%
Making Project Structure (Classes, logic folder design) | 33 | 20 | 33 | 20 | 100%
Basic Social Media Platform (user login,logout,registration) | 38 | 15 | 38 | 15 | 100%
Making the actual functionality (playing games,points system) | 53 | 30 | 53 | 30 | 5%
Cleaning up bugs, fixing, little features | 38 | 83 | 38 | 83 | 70%
Project Documentation | 1 | 67 | 1 | 67 | 85%